## Sheet1
Sprints 2 tasks
Categories: | Description: | Collaborators: | Date completed: | Time to complete:
Controllers | Implement keyboard controller | Saurav & Harry | 2025-02-06 | 6
| Implement mouse controller | Saurav & Harry | 2025-02-03 | 5
Entities | Implement Entity class | Saurav & Harry & Payton | 2025-02-06 | 8
| Implement Player class | Saurav & Payton | 2025-02-06 | 12
| Implement Mob class | Saurav & Payton & Harry | 2025-02-17 | 17
| Implement Projectile class | Saurav & Payton & Leo & Doaping | 2025-02-10 | 10
| Implement Block class | Doaping & Leo & Harry | 2025-02-16 | 12
| Implement Pickup Item class | Harry | 2025-02-05 | 11
| Implement Rocket class | Doaping & Leo | 2025-02-06 | 9
| Implement Sniper class | Doaping & Leo | 2025-02-06 | 8
| Implement Shotgun class | Doaping & Leo & Payton | 2025-02-13 | 9
Commands | Create ICommands Interface | Harry | 2025-02-05 | 8
| Implement Action Commands | Saurav & Payton & Leo & Doaping | 2025-02-09 | 12
| Implement Graphics Commands | Saurav & Harry | 2025-02-05 | 7
| Implement Game Commands | Saurav | 2025-02-05 | 6
| Implement Command Requester | Saurav | 2025-02-04 | 6
| Implement Movement Commands | Saurav | 2025-02-03 | 5
Graphics | Implement Static Sprites | Saurav & Harry | 2025-02-05 | 8
| Implement Animated Sprites | Harry & Leo & Payton & Daoping | 2025-02-17 | 14
| Implement Text Sprites | Harry | 2025-02-05 | 6
| Create Sprite Sheet(s) | Harry | 2025-02-05 | 6
Managers | Implement Game Manager | Saurav & Harry | 2025-02-05 | 7
| Implement Sprite Manager | Saurav | 2025-02-03 | 6
Project Management | Create map for inheritance trees | Alex | 2025-02-14 | 6
| Create map for class interactions | Alex | 2025-02-15 | 7
| Create tasks sheet | Alex & Saurav | 2025-02-12 | 7
Misc. | Menu | Saurav | 2025-02-17 | 5